Tentative 10-Week Summer Project Plans

# Week 1: Orientation and Facility Familiarization

Students will become familiar with the research environment, including facility layout, safety procedures, and access requirements such as badging. Orientation sessions will introduce the project goals, expectations, and available computational resources. Students must set up GitHub repositories (not the main fork) and prepare a brief introductory presentation summarizing their understanding of the project.

# Week 2: Fundamentals of Algorithms and Environment Setup

Students will configure the computational environment and gain access to CHESS clusters or HPC systems. Students will learn the fundamentals of different algorithms.

- Configure computational environment

- Gain access to CHESS clusters / HPC systems

Tasks:Learn the fundamentals of key algorithms

Aditya: Bayesian Optimization & Active Learning

- Concepts of algorithm

- Feature extraction and feature selections

- Workflow

- How the real time measurement can be done with BO and active learning

Olivia & Max: Clustering

- Clustering concepts

- Feature extraction and feature selections

- What is clustering, types (example: K-means, DBSCAN, GMM, Hierarchical,),

- when to use,

They will present their findings in a short slide presentation.

# Week 3: Data Understanding and Access

Introduction of data format - Students will identify where the data is stored and understand file formats such as HDF5 and .nxs files.

Topics

- Data storage location

- File formats:

  - .cbf

  - HDF5 (.h5)

  - NeXus (.nxs)

Tasks:
	Aditya:

- Python code to import data from multiple folders

- Import pipeline automates ingestion from multiple folders

  - Handle .cbf raw files

Olivia:

- Learn file structure, shapes, trees

- import pipeline Automated data loading of .nxs files

Max:

- Python code to import data from multiple folders

- Import pipeline automates ingestion from multiple folders with specific raw .cbf files.

# Week 4: Data Analysis : BO and Clustering Implementation

Tasks:
	Aditya

- statistical analysis

- Mean intensity comparison

- Standard deviation comparison

- Min/Max intensity ranges

- Total integrated intensity

- Number of non-zero pixels

- Median values

- Intensity ratios (total, peak, mean)

- Correlation coefficient

- RMS difference

Olivia & Max:

- Implement clustering:

  - K-Means,

  - DBSCAN,

  - GMM

  - Agglomerative

  - others

They will analyze how each algorithm suggests measurement strategies such as cluster centers, boundaries, or uncertain regions.

# Week 5–6: Advanced Methods and Integration

Additya will implement advanced approaches including Hybrid Random Forest, uncertainty-based Active Learning, and Bayesian Optimization strategies (Expected Improvement, Upper Confidence Bound, Probability of Improvement). Students will evaluate exploration vs exploitation trade-offs and design batch experiment strategies.

Task:

Aditya:BO & Active Learning

Implement:

- Feature extraction and feature selections

- Uncertainty quantifications

- Expected Improvement (EI)

- Upper Confidence Bound (UCB)

- Probability of Improvement (PI)

- Different model?

- Hybrid Random Forest models

Design:

- Exploration vs exploitation strategies

- Batch experiment recommendations

Olivia: Advanced Clustering

- parameter tuning - automated selections

- CPU/GPU comparison, time analysis

- Building an AI agent to automate clustering decisions.

Max: Clustering + Active Learning Integration

-Feature extraction and feature selections

- Pattern-aware clustering

- Physics-informed modeling

- Uncertainty-based strategy

# Week 7: Generalization to New Datasets

Students will test all developed pipelines on new datasets, ensuring robustness and adaptability. They must verify the code handles variable dataset structures and conditions.

- Apply methods to new dataset

- Ensure adaptability

- Apply anything we missed

# Week 8: Report Writing

Students will begin drafting a comprehensive report including introduction, methodology, results, and comparisons. Documentation of code and workflows is required.

| Task | Deliverable |
| --- | --- |
| Apply all methods to new dataset | Validated results |
| Test robustness | Working pipelines |

# Week 9–10: Finalization and Presentation

Students will generate final plots, analyze results, and complete their reports. They will prepare and deliver a final presentation summarizing their work, findings, and conclusions.

| Task | Deliverable |
| --- | --- |
| Generate plots and results | Final figures |
| Finalize report | Completed report |
| Prepare presentation | Slides + talk |

# Weekly Requirements

Students must update their GitHub repositories weekly (not main fork), create presentation slides, and demonstrate progress consistently. Emphasis is placed on explaining why algorithms were chosen and evaluating their performance.